## Registration
Time sheet
All rise!
Group: [name group]
Date | Task | Worked on | Employee | Hours | Description
2020-05-05 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 3 | first questions to the company and the app ideas
2020-05-06 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 2 | discussing preparation for friday meeting with client
2020-05-07 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 2 | Discussing the ideas we thought of during a previous meeting
2020-05-10 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 1.5 | Discussed the project plans
2020-05-11 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 3 | Finalized main idea
2020-05-15 | START-Startup of project | Documentation | Bjarne ten Bolscher | 1.5 | created wireframe for the shop
2020-05-15 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 2 | discussion on functional design
2020-05-19 | START-Startup of project | Documentation | Bjarne ten Bolscher | 2 | Designed leaderboard wireframes
2020-05-26 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | working on the challenges home page aswell as getting back into working with Vue
2020-05-27 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | working on the challenges home page aswell as getting back into working with Vue
2020-05-28 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 6 | made the cards for the overview of the challenges
2020-05-29 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | putting some finishing touch on the design
2020-06-01 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | Vue.js tutorials
2020-06-02 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | CSS/ Vue.js tutorials on images/ icons
2020-06-04 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | Added some basic design to the buttons.
2020-06-08 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | Creating challenge page
2020-06-09 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | making the Timer for the challenge page aswell as the popUP
2020-06-10 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | changed some things in the challegne page and merge it with the master
14/5/2020 | MEETING-Sprint 0 discussions | Design | Bjarne ten Bolscher | 1 | discussing the high level design with the team and supervisor
30/5/2020 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | Changed the style of the challenge cards to look better
2020-06-12 | MEETING-Project work/meetings | Implementation | Bjarne ten Bolscher | 1 | stand up
2020-06-12 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 4 | create API to post a challenge
2020-06-12 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | Create API to update the challenge
13-6-2020 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 5 | Tried to get the APi for the update correct can't seem to get it to work
2020-06-13 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | get the challenge page to show correct data.
2020-06-13 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 1 | With help from Ivo updating the challenges works now
2020-06-15 | Sprint1-Project work/meetings | Implementation | Bjarne ten Bolscher | 2 | stand-up
2020-06-15 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | Make the challenge page not ask for all the challegnes/users
2020-06-15 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 4 | Make the challenge page actually show to names of the participants (took this long cus of async hijinks)
2020-06-18 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | Fixed some issues with the new code added and merged it to the master
2020-06-19 | Sprint1-Project work/meetings | Review | Bjarne ten Bolscher | 1 | grp meeting
2020-06-19 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | Add a sort of filter to the waitingroom had some trouble with the api
2020-06-19 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | Change the popup for the creation of challenges to have a dropdown
2020-06-19 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 1 | changed the timer to work better
2020-06-19 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 4 | made a base for the fixed challenges tab
2020-06-22 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 1 | stand up
2020-06-22 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 4 | final touches to the fixed challenges tab
2020-06-24 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 4 | worked on getting the fitbit id instead of a static id
2020-06-24 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 1.5 | stand up
2020-06-25 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 5 | worked on some bugs with the fitbit id
2020-06-25 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 1 | stand up
2020-06-26 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 1 | standup
2020-06-27 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 2 | helped fix some bugs
2020-06-29 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 3 | stand up
2020-06-29 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 2 | Looked into some of the bugs
2020-07-01 | MEETING-Project work/meetings | Review | Bjarne ten Bolscher | 2 | stand up
2020-07-01 | WORK-Sprint 1 project work | Review | Bjarne ten Bolscher | 2 | Stand up meeting
2020-07-01 | WORK-Sprint 1 project work | Implementation | Bjarne ten Bolscher | 3 | Final changes to the project
2020-07-01 | Sprint1-Project work/meetings | Implementation | Bjarne ten Bolscher | 2 | bug fixes
2020-05-05 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 1 | first questions to the company and app ideas
2020-05-14 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 1 | discussing the high level design with the team and supervisor
2020-06-05 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 1 | discussing preparation for friday meeting with client
2020-07-05 | START-Startup of project | Design | Giovanni Dave Tjandra | 0.5 | Design image for badge collecting app solution
2020-07-05 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 2 | Rediscussing ideas to implement
2020-10-05 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 1 | Discussing initial idea and plan of approach
2020-11-05 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 2.5 | Finalizing main idea and competences
14/5/2020 | START-Startup of project | Documentation | Giovanni Dave Tjandra | 3 | short high level design
15/5/2020 | MEETING-Sprint 0 discussions | Design | Giovanni Dave Tjandra | 2 | discussion on functional design
18/5/2020 | MEETING-Sprint 0 discussions | Documentation | Giovanni Dave Tjandra | 2 | functional design edit
19/5/2020 | START-Startup of project | Design | Giovanni Dave Tjandra | 3 | wireframe challenge page
2020-03-06 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 1 | Bell tutorial
2020-05-03 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 6.5 | fitbit auth changed moduls
2020-05-05 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 1 | first questions to the company and the app ideas
2020-05-20 | START-Startup of project | Documentation | Hassan Babiker | 2.5 | Research fitbit devices and what they can do for our challenges
2020-05-29 | Sprint1-Project work/meetings | Implementation | Hassan Babiker | 4 | setting up back-end
2020-06-01 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 2 | heroku deployment
2020-06-03 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 7 | fitbit OAuth
2020-06-05 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 0.5 | brainstorming ideas for a solution
2020-06-05 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 1 | discussing preparation for friday meeting with client
2020-07-05 | MEETING-Sprint 0 discussions | Documentation | Hassan Babiker | 0.5 | Prepare Presentation
2020-09-06 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 3.5 | Updated sign-in page
2020-10-05 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 1 | Discussing initial idea and plan of approach
2020-10-06 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 6 | integrate fitbit
2020-11-05 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 2.5 | Finalizing idea
2020-12-05 | START-Startup of project | Design | Hassan Babiker | 1 | discussing the high level design with the team and supervisor
14/5/2020 | START-Startup of project | Documentation | Hassan Babiker | 2 | worked on functional design and plan of aproach
15/5/2020 | START-Startup of project | Design | Hassan Babiker | 1 | Sketch
15/5/2020 | MEETING-Sprint 0 discussions | Design | Hassan Babiker | 3 | teacher feed back on deleveries and team discussions
19/5/2020 | START-Startup of project | Design | Hassan Babiker | 1 | Meeting to review tasks
19/5/2020 | START-Startup of project | Documentation | Hassan Babiker | 3 | wrote fitbit documentaion
29/5/2020 | Sprint1-Project work/meetings | Implementation | Hassan Babiker | 0.5 | standup
29/5/2020 | Sprint1-Project work/meetings | Implementation | Hassan Babiker | 1 | hapi tutorial
2020-12-06 | MEETING-Project work/meetings | Implementation | Hassan Babiker | 1 | stand up
13/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 3 | integrating fitbit data with front-end
14/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 4 | Auth0 , Vuex ,Vue turorial research
14/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 3 | integrating fitbit data with Auth0 -,Vuex, Vue
15/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 12 | integrating fitbit data with Auth0 -,Vuex, Vue
16/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 4 | fitbit integration error fix
18/6/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 9 | OpenID Connect documentaion and grant flow + Signin page + Fitbit Authurization and user profile data + navigation control +
19/6/2020 | Sprint1-Project work/meetings | Review | Hassan Babiker | 1 | grp meeting
21/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 5 | Finishing fitbit integ
22/06/2020 | WORK-Sprint 1 project work | Review | Hassan Babiker | 1 | Review with team
23/06/2020 | WORK-Sprint 1 project work | Review | Hassan Babiker | 1 | Stand-up
23/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 2 | update login card
23/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 5 | research deployment options and how to implement with gitlab ci
24/6/2020 | MEETING-Project work/meetings | Review | Hassan Babiker | 1 | Stand-up
24/6/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 3 | Revoking user access
25/6/2020 | MEETING-Project work/meetings | Review | Hassan Babiker | 1 | standup
25/6/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 15 | Heroku docker setup and pipe lines and Implementing getlab ci to build docker files front-end and back-end to respective heroku apps + fixing vue mounting issue
26/06/2020 | MEETING-Project work/meetings | Implementation | Hassan Babiker | 1 | helping with debuggin merging issue
27/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 6 | fixing bugs
28/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 6.5 | fixing bugs
29/06/2020 | WORK-Sprint 1 project work | Review | Hassan Babiker | 3 | Meeting
29/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 7 | fixing user not auth activity + bugs
30/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 3 | fixing cloud databse related issue
30/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 4 | reading on vue component cycle + trying to fix value undefined bug
30/06/2020 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 2 | fixed challenge functionality
2020-01-05 | Sprint1-Project work/meetings | Review | Ivo Tasev | 0.5 | Standup session end of sprint 1
2020-01-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 0.5 | looking up Vue.js docs and libraries
2020-01-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 0.5 | fixing little bugs with frontend
2020-01-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 1 | merging branches for snapshot
2020-01-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 1.5 | connecting leaderboards page with REST API
2020-01-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 1.5 | connecting challenges page with REST API
2020-01-06 | WORK-Sprint 1 project work | Documentation | Ivo Tasev | 1.5 | finishing up on technical design
2020-01-06 | WORK-Sprint 1 project work | Documentation | Ivo Tasev | 1.5 | making the sprint 1 retrospective
2020-05-05 | MEETING-Project work/meetings | Documentation | Ivo Tasev | 0.5 | creating a template for plan of approach
2020-05-05 | MEETING-Sprint 0 discussions | Design | Ivo Tasev | 1 | brainstorming ideas for a solution
2020-05-06 | WORK-Sprint 1 project work | Documentation | Ivo Tasev | 1.5 | Creating presentation for end of Srint 1
2020-06-05 | MEETING-Sprint 0 discussions | Design | Ivo Tasev | 1 | going over questions and ideas
2020-08-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 3 | Reading up on Docker
2020-09-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 6 | Expanding REST API and database
2020-10-05 | MEETING-Sprint 0 discussions | Design | Ivo Tasev | 1 | Discussion on main idea and PoA
2020-11-05 | START-Startup of project | Design | Ivo Tasev | 2.5 | Finalizing main idea and competences
14/5/2020 | MEETING-Sprint 0 discussions | Documentation | Ivo Tasev | 2 | Adding MoSCoW requirements
20/05/2020 | MEETING-Sprint 0 discussions | Documentation | Ivo Tasev | 2 | Cleaning up documentation
24/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 2 | Creating initial project
26/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 1.5 | Creating model classes
26/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 1.5 | Creating database
26/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 2 | Designing database
29/05/2020 | Sprint1-Project work/meetings | Review | Ivo Tasev | 0.5 | Standup session
29/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 4 | Docker and AWS research
30/05/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 1 | Merging database and model classes branch
2020-12-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 1 | stand up/meeting
2020-10-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 6 | Brushing up on vue
2020-11-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 4 | Merging and connecting a stable version for demo
2020-11-06 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 2 | Creating presentation for client
14/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 7 | Trying to make webpack work, reading up on it
17/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 8 | Reading up on docker
19/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 5 | Containerization for frontend
20/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 9 | Containerization for frontend + backend + database
20/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 2 | Connecting all containers in a docker-compose file
19/06/2020 | Sprint1-Project work/meetings | Implementation | Ivo Tasev | 1 | Stand-up
22/06/2020 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1 | stand-up/review
23/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 1 | Merging branches
23/06/2020 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1 | daily stand-up
23/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 6 | fixed backend starting before database, causing a crash and requiring a reboot
24/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 6 | making gitlab ci work with docker-compose
24/06/2020 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1 | daily stand-up
24/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 3.5 | fixing nginx config issue with docker
25/06/2020 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1 | daily stand-up
25/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 5 | Adding user to databse on log-in
29/06/2020 | WORK-Sprint 1 project work | Implementation | Ivo Tasev | 7 | Fixing some functionality bugs, merging changes
29/06/2020 | MEETING-Project work/meetings | Implementation | Ivo Tasev | 1 | Daily stand up
29/06/2020 | MEETING-Project work/meetings | Implementation | Ivo Tasev | 2 | brainstorming an issue
30/06/2020 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1.5 | Daily stand up
2020-01-07 | WORK-Sprint 1 project work | Review | Ivo Tasev | 1 | Daily stand up
2020-01-07 | WORK-Sprint 1 project work | Documentation | Ivo Tasev | 4 | Adding security part in tech. documentation
2020-01-07 | WORK-Sprint 1 project work | Documentation | Ivo Tasev | 3 | Preparing final presentation
2020-01-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 2 | prepared leaderboard to connect to backend
2020-04-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 13 | Created and finished navigation bar for pages
2020-05-05 | MEETING-Sprint 0 discussions | Design | Wim Luyendijk | 1 | first questions to the company and app ideas
2020-05-06 | MEETING-Project work/meetings | Documentation | Wim Luyendijk | 1 | Sprint review with company
2020-05-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 6 | Fixed navigation bar bug on progress page and researched UX
2020-06-05 | MEETING-Sprint 0 discussions | Design | Wim Luyendijk | 1 | Went over questions and Ideas
2020-07-05 | START-Startup of project | Documentation | Wim Luyendijk | 1 | Detailed and developed idea for all rise solution
2020-07-05 | MEETING-Sprint 0 discussions | Design | Wim Luyendijk | 2 | polished ideas before company meeting
2020-07-05 | START-Startup of project | Documentation | Wim Luyendijk | 3 | Made wire frames for company meeting
2020-07-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 6 | Made sorting algorythm for leaderboard and added near user idea
2020-08-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 6 | Added ranks to leader board, created progress bars for progress page
2020-10-05 | MEETING-Sprint 0 discussions | Design | Wim Luyendijk | 1 | Discussed division of competencies and refined project solution
2020-10-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 5 | Connected progress page to back end.
2020-10-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 3 | connected pages together and matched pages to house style
2020-11-05 | MEETING-Sprint 0 discussions | Design | Wim Luyendijk | 2.5 | Finalized main idea solution
2020-11-06 | MEETING-Project work/meetings | Implementation | Wim Luyendijk | 1 | helped with navigation of sign in page
2020-11-06 | START-Startup of project | Design | Wim Luyendijk | 2 | Reasearched Vuetify
2020-12-05 | START-Startup of project | Documentation | Wim Luyendijk | 2 | Worked on functional design documentation
14/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 1 | Meeting about Functional Design doc & plan of approach
14/5/2020 | START-Startup of project | Documentation | Wim Luyendijk | 3 | Created DataFlow diagrams for Functional Design
15/5/2020 | START-Startup of project | Documentation | Wim Luyendijk | 1 | Finished and added DataFlow diagrams to Functional Design
15/5/2020 | START-Startup of project | Documentation | Wim Luyendijk | 1 | Wrote descritptions for wire frames
15/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 3 | Fixed functional document, added challenge form
17/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 0.5 | Finished competencies for plan of approach and functional design
18/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 1 | Divided tasks & reasserted functional Design
18/5/2020 | START-Startup of project | Design | Wim Luyendijk | 1 | discussed color theory with game designer for UI/UX
18/5/2020 | START-Startup of project | Design | Wim Luyendijk | 2 | Designed progress page & project color pallets
19/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 1 | Meeting to review tasks
19/5/2020 | START-Startup of project | Design | Wim Luyendijk | 1 | Made revisions to design based from meeting
20/5/2020 | MEETING-Sprint 0 discussions | Documentation | Wim Luyendijk | 1 | meeting with teacher for functional design
20/5/2020 | START-Startup of project | Design | Wim Luyendijk | 4.5 | Worked on application desing & style
21/5/2020 | START-Startup of project | Documentation | Wim Luyendijk | 5 | wrote documentation of pages and detailed page designs
22/5/2020 | START-Startup of project | Documentation | Wim Luyendijk | 1 | Changed functional design to match teacher comments
25/5/2020 | MEETING-Project work/meetings | Documentation | Wim Luyendijk | 1 | helped write issues and divided tasks
26/5/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 5 | got used to Vue, and added Vue routing to support multiple pages
27/5/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 6 | Finished layout for Leader board
28/5/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 4 | Added dynamic coloring to leader board
31/5/2020 | WORK-Sprint 1 project work | Test | Wim Luyendijk | 1 | Got test user feed back on Leaderboard look and feel
2020-12-06 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 7 | Added Vuetify to project, and converted navigation bar to v components
13/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 9 | fixhed navigation bugs and changed leaderboard to vuetify
14/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 11.5 | converted progresspage layout to vuetify, and challenge winner pop up
14/6/2020 | WORK-Sprint 1 project work | Test | Wim Luyendijk | 1 | Got feed back from test users on layout
16/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 8 | Added Daily goal popup and integrated daily goal database updater
16/6/2020 | WORK-Sprint 1 project work | Test | Wim Luyendijk | 1 | Got test user feed back on Daily goal pop ups
17/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 5 | Added type checking to daily goal input and fixed rendering bug
18/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 8 | Matched all pop-ups to match house styling and fixed merge rending issues
19/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 4 | fixed bugs and worked on progress page layout issues
21/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 10 | created use coupon pop up and updated used coupons on database
22/6/2020 | MEETING-Project work/meetings | Review | Wim Luyendijk | 1 | Discussed what needed to be done for final leg of sprint
22/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 6 | added popup on progress when another user activated their coupon
23/6/2020 | MEETING-Project work/meetings | Review | Wim Luyendijk | 1 | Disucssed progress of final sprint and what was left/divided tasks
23/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 5 | Fixed Remaining coupon Pop Up bugs discoverd in meeting
24/6/2020 | MEETING-Project work/meetings | Review | Wim Luyendijk | 1 | Planned approach of tasks remaining in sprint/stand up
24/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 9 | Added support for application use on mobile
25/6/2020 | WORK-Sprint 1 project work | Documentation | Wim Luyendijk | 3 | Worked wireframes for final documentation
26/6/2020 | MEETING-Project work/meetings | Review | Wim Luyendijk | 1 | worked witht the team on resovling bugs in application
26/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 3 | Finalized mobile application layout and used CI to push to webpage
27/6/2020 | WORK-Sprint 1 project work | Review | Wim Luyendijk | 5 | worked on bug fixes and final documentation
28/6/2020 | WORK-Sprint 1 project work | Review | Wim Luyendijk | 4 | worked with babi in trying to get bugs fixed on web page
29/6/2020 | MEETING-Sprint 0 discussions | Review | Wim Luyendijk | 3 | Worked with team to try to smash bugs on webpage and merge branches
29/6/2020 | WORK-Sprint 1 project work | Documentation | Wim Luyendijk | 1 | Worked on wireframes for final documentation
29/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 4 | Finished breaking bug fixes and helped final bug fixing
30/6/2020 | MEETING-Project work/meetings | Review | Wim Luyendijk | 2 | Discussed final pushes for project and helped debug code
30/6/2020 | WORK-Sprint 1 project work | Documentation | Wim Luyendijk | 7 | Finalized Wireframes and worked on final functional design documentation
30/6/2020 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 1 | Worked with Babi to get Web applicaiton running smoothly online
2020-01-07 | WORK-Sprint 1 project work | Implementation | Wim Luyendijk | 8 | Finalized documentation and fixed remianing bugs
2020-05-06 | MEETING-Sprint 0 discussions | Design | Yang Lin | 1 | Went over questions and Ideas
2020-05-07 | MEETING-Sprint 0 discussions | Design | Yang Lin | 2 | Polishing ideas we discussed before
2020-05-10 | MEETING-Sprint 0 discussions | Design | Yang Lin | 1 | Discussing Minimal Viable product
2020-05-11 | MEETING-Sprint 0 discussions | Design | Yang Lin | 2.5 | Finalizing main idea and competences
2020-05-15 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 3 | Wireframe for progress page on functional design + meeting
2020-05-17 | START-Startup of project | Documentation | Yang Lin | 1 | Rewrote the challenge system
2020-05-18 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1.5 | Meeting and feedback on functional design + redivision of tasks
2020-05-19 | START-Startup of project | Documentation | Yang Lin | 0.5 | Fixed some issues with the rewritten challenge system
2020-05-19 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1 | Meeting and showing progress on tasks for functional design
2020-05-25 | MEETING-Sprint 0 discussions | Design | Yang Lin | 1 | Meeting and beginning of dev phase + division of tasks
2020-05-28 | WORK-Sprint 1 project work | Implementation | Yang Lin | 4 | Start local vue project and work on create challenges pop up form
2020-05-28 | WORK-Sprint 1 project work | Implementation | Yang Lin | 6 | Watching videos and reading documentation learning vue js
2020-05-30 | MEETING-Sprint 0 discussions | Review | Yang Lin | 1 | Stand up meeting
2020-06-02 | WORK-Sprint 1 project work | Implementation | Yang Lin | 3 | Try to make the pop up match but its not vuetified yet
2020-06-05 | MEETING-Project work/meetings | Review | Yang Lin | 1.5 | Brainstorm and meeting with the client
2020-06-08 | WORK-Sprint 1 project work | Implementation | Yang Lin | 3 | Going a bit deeper into vue
2020-06-11 | WORK-Sprint 1 project work | Implementation | Yang Lin | 2 | Starting to fresh up on mysql for backend
2020-06-11 | MEETING-Project work/meetings | Review | Yang Lin | 0.5 | MVP presentation
2020-06-08 | MEETING-Project work/meetings | Review | Yang Lin | 1 | Meeting with tristan and group
2020-06-12 | MEETING-Project work/meetings | Implementation | Yang Lin | 1 | Meeting with tristan and group
2020-06-13 | WORK-Sprint 1 project work | Implementation | Yang Lin | 4 | Check the API for updating work and try to fix challenge list as it can only hold 3
2020-06-14 | WORK-Sprint 1 project work | Implementation | Yang Lin | 2 | Having issues testing API calls and getting backend running after dling from master
2020-06-15 | MEETING-Project work/meetings | Review | Yang Lin | 1.5 | Meeting tristan + group and fixed issues with running backend
2020-06-17 | WORK-Sprint 1 project work | Implementation | Yang Lin | 3 | Making coupons seperated from challenges and researching API calls
2020-06-19 | MEETING-Project work/meetings | Review | Yang Lin | 1 | Meeting with tristan and group after feedback sprint 2
2020-06-18 | WORK-Sprint 1 project work | Implementation | Yang Lin | 5 | Reading up on sql more making the queries for coupons
2020-06-20 | WORK-Sprint 1 project work | Implementation | Yang Lin | 3 | Finished up the new DB with coupons and the API calls for them
2020-06-22 | MEETING-Sprint 0 discussions | Review | Yang Lin | 1 | Meeting tristan and group
2020-06-23 | WORK-Sprint 1 project work | Review | Yang Lin | 2 | Going through all Challenges related files writing a description of how it works for docs
2020-06-23 | WORK-Sprint 1 project work | Review | Yang Lin | 2 | Going through Progress page files including coupons and daily goal to work on docs later
2020-06-24 | WORK-Sprint 1 project work | Review | Yang Lin | 4 | Going through fitbit and write the new format for technical design
2020-06-25 | WORK-Sprint 1 project work | Implementation | Yang Lin | 2 | Complete writing about Challenges, Fitbit and progress page
2020-06-26 | WORK-Sprint 1 project work | Implementation | Yang Lin | 4 | Create new flowchart for the technical design and replace the old dataflow diagrams
2020-06-23 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1 | Meeting group discussing progress final sprint and tasks
2020-06-24 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1 | Daily stand up
2020-06-25 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1 | Daily stand up
2020-06-26 | MEETING-Sprint 0 discussions | Documentation | Yang Lin | 1 | Daily stand up
2020-06-26 | WORK-Sprint 1 project work | Documentation | Yang Lin | 4 | Create new database design for technical design
2020-06-27 | WORK-Sprint 1 project work | Documentation | Yang Lin | 3 | Create new class diagram for technical design
2020-06-26 | WORK-Sprint 1 project work | Documentation | Yang Lin | 0.5 | Removed shop from technical design and remade flowchart
2020-06-30 | MEETING-Sprint 0 discussions | Review | Yang Lin | 1 | Stand up meeting
2020-07-01 | MEETING-Sprint 0 discussions | Review | Yang Lin | 2 | Stand up meeting
2020-06-30 | WORK-Sprint 1 project work | Implementation | Yang Lin | 4 | Finishing technical design
2020-06-29 | MEETING-Sprint 0 discussions | Review | Yang Lin | 1 | Stand up meeting
2020-01-07 | WORK-Sprint 1 project work | Implementation | Hassan Babiker | 11 | Implementing fixed challenge func for most steps challenge and Burner
Usage instructions
1 Make sure to fill in the DATA tabs below with the correct information
2 Use the sheet on the left to register working hours
3 View the overview tabs (automatically updated)

## Overview - employees
Sum of Hours
| Giovanni Dave Tjandra | Wim Luyendijk | Ivo Tasev | Yang Lin | Bjarne ten Bolscher | Hassan Babiker | Total
Design | 14 | 18 | 5.5 | 7.5 | 14.5 | 12 | 71.5
Documentation | 5 | 37.5 | 16 | 18.5 | 3.5 | 8 | 88.5
Implementation |  | 155.5 | 102.5 | 46 | 91 | 138 | 533
Review |  | 18 | 7.5 | 19.5 | 13.5 | 8 | 66.5
Total | 19 | 229 | 131.5 | 91.5 | 122.5 | 166 | 759.5
Sum of Hours
Overview employees
Hours per userstory
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Usage instructions
1. "Right-click" -> "Refresh" to refresh the pivot table on the left
2. Make sure to filter out blank lines in the slicer below
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Overview - tasks
Sum of Hours
| Design | Documentation | Implementation | Test | (leeg) | Review | Total
MEETING-Project work/meetings |  | 2.5 | 8 |  |  | 24 | 34.5
START-Startup of project | 19.5 | 32.5 |  |  |  |  | 52
(leeg)
MEETING-Sprint 0 discussions | 52 | 23.5 |  |  |  | 9 | 84.5
WORK-Sprint 1 project work |  | 30 | 502.5 | 3 |  | 30.5 | 566
Sprint1-Project work/meetings |  |  | 22.5 |  |  | 3 | 25.5
Total | 71.5 | 88.5 | 533 | 3 |  | 66.5 | 762.5
Overview userstories
Hours per category
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Usage instructions
1. "Right-click" -> "Refresh" to refresh the pivot table on the left
2. Make sure to filter out blank lines in the slicer below

## DATA - User stories
ID | Description | ID-Description
START | Startup of project | START-Startup of project
MEETING | Sprint 0 discussions | MEETING-Sprint 0 discussions
MEETING | Project work/meetings | MEETING-Project work/meetings
Sprint1 | Project work/meetings | Sprint1-Project work/meetings
US-1.2 | Description of user story 1.2 | US-1.2-Description of user story 1.2
US-2.1 | Description of user story 2.1 | US-2.1-Description of user story 2.1
US-2.2 | Description of user story 2.2 | US-2.2-Description of user story 2.2
WORK | Sprint 1 project work | WORK-Sprint 1 project work
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Usage instruction
Enter ID en Description
Note: Column ID-Description is automatically filled in

## DATA - Type tasks
Type tasks
Design
Documentation
Implementation
Test
Review
…
Usage instruction
Enter type of tasks
Note: Try to keep this list short!

## DATA - Employees
Name | Tel | Email
Giovanni Dave Tjandra | +31 633 862 503 | 445963@student.saxion.nl
Hassan Babiker |  | 462644@student.saxion.nl
Bjarne ten Bolscher | 646556791 | 466348@student.saxion.nl
Wim Luyendijk | +31 6 17998254 | 445662@student.saxion.nl
Ivo Tasev | +359 899835350 | 469297@student.saxion.nl
Yang Lin |  | 450968@student.saxion.nl
Usage instruction
Enter Name, Telephone number and email